## Sheet1
Risk Details |  | Risk Identification |  |  |  |  | Response Strategy |  |  |  |  | Reflection
Risk ID | Date Identified | Name Of Risk | Risk Description | Probability | Impact | Stage Of Project | Strategy To Mitigate | Risk Occured | When did it occur | Action Taken | Length Of Impact | Future Risk
1 | 18-12-2020 | Lack of knowledge | Being new to the industry and learning from scratch | High | Medium | Continuous | Work hard and follow through on plans and practice | Y | Points throughout the project that were unlcear to me | Read through QA Community, contacted Vinesh and Aswene for guidence | 3hours | This will always be risk - however reflection on what was learned can mitigate this secific risk happened again
2 | 18-12-2020 | Internet Connection | If internet provider goes down during work or presentation | Medium | High | Continuous | get in touch with QA to explain situation, then phone provider | Y | Mainly from 19th - 21st January | Resetting the connection because it would drop randomly through the day | 1hour | There is always the possibility that you will lose connection, just make sure that everything you have is always backed up
3 | 18-12-2020 | Computer Breaking | computer could crash or have something spilled on to it | Medium | Medium | Continuous | get in touch with QA to explain situation, then repair/purchase new | N | Risk did not occur | No action needed | No Impact | There is always the possibility that something will break, you just make sure that everything you have is always backed up
4 | 19-12-2020 | Time Management | Dont want to leave everything to the last minute | Low | High | Continuous | create a schedule with deadlines to hit for myself | N | Risk did not occur | No action needed | No Impact | Getting complaicent - you only hit the targets because you set them and work well to hit them, do not become complaicent
5 | 19-12-2020 | Scope Creep | make sure that we are sticking to the brief | Low | High | Continuous | create user stories using brief and follow them through the development | N | Risk did not occur | No action needed | No Impact | Make sure you deliver to the letter what the client asks for, if this means asking questions for clarification, then do so
6 | 19-12-2020 | Home Working | Adequate breaks from computer, good working station | Medium | Medium | Continuous | Make sure work station is fuctional - make sure allocation for breaks are taken | N | Risk did not occur | No action needed | No Impact | Home working is becoming more and more the norm - its something that we all have to get used to
7 | 28-12-2020 | Covid - 19 pandemic | Current global pandemic | Low | High | Continuous | Reduce encounters and dont mke unnessarcery journies | N | Risk did not occur | No action needed | No Impact | Hopefully there wont be one similar to this - but there is always the risk that another pandemic will happen
8 | 2021-07-01 | Tech incompatability | Software downloads | Low | Medium | Continuous | always download a stable version of the software - not latest version as not everthing may be compatible with it | Y | Right at the start when we were learning coverage | reversed version of java to 14, not 15 as 15 didnt support coverage | 30mins | alwasys be aware that the latest software can also be the buggiest/not what you want
9 | 2021-10-01 | Merge conflicts | conflicts in code that could dely rollout | Medium | High | Continuous | Make sure that all work is megered into dev in plenty of time to allow for conflict resolution | N | Risk did not occur | No action needed | No Impact | Working on one document at a time was a good way to keep merge conflicts at bay, it was easier because it was an individual project